☦  ☦  ☦

ETHIOPIAN ORTHODOX TEWAHEDO CHURCH

Next-Generation Digital Platform

Phased Roadmap & Architecture

| Scope | Full build plan: from Day 1 to Launch and beyond |
| --- | --- |
| Timeline |  |
| Audience | Steering Committee, Technical Leads, Design Team, MK Partnership |

PART 1 — VISION & STRATEGIC PRINCIPLES

# 1. The Problem We Are Solving

The EOTC has 60M+ faithful worldwide. Its current website (ethiopianorthodox.org) was built in 2003 and is:

- Unresponsive — does not work on mobile or tablets

- Disconnected — no donations, no church finder, no events, no user accounts

- Static — hand-coded HTML with no CMS, search, or notifications

- Outdated — GIF navigation, no Ge'ez rendering, no accessibility

This platform must surpass the Coptic Orthodox Church, Greek Orthodox Archdiocese, and Mahibere Kidusan in digital reach and quality.

# 2. The Four Pillars

| Pillar | Goal |
| --- | --- |
| 1 — SUSTAIN | Digital Giving Portal: fund churches, monasteries, and missions globally |
| 2 — CONNECT | Church Finder & Events: connect faithful to their nearest parish |
| 3 — INFORM | News Hub: authoritative EOTC and pan-Orthodox news in Amharic + English |
| 4 — EDUCATE | Tewahedo Academy: structured theological education for all ages |

# 3. Guiding Principles

| Principle | What It Means |
| --- | --- |
| Ethiopia First, Diaspora Ready | Must work at 3G speeds on older Android devices. Performance is a core requirement. |
| Content Before Complexity | Migrate all existing content first. Great content beats feature-rich empty pages. |
| Modular by Design | Each pillar is independent. A delay in one does not block the others. |
| Church-Owned | Diocese and parish admins manage their own content without developer help. |
| Ge'ez First | Amharic and Ge'ez must render correctly on all platforms before anything ships. |

PART 2 — SYSTEM ARCHITECTURE

# 4. Architecture at a Glance

| Layer | Technology / Description |
| --- | --- |
| Frontend | Next.js (React) — SSR, PWA, i18n (Amharic, English, Tigrinya, Ge'ez) |
| CMS | Strapi (headless) — role-based: Super Admin → Synod → Diocese → Parish → Contributor |
| LMS | Moodle (self-hosted, EOTC-themed) — courses, quizzes, certificates |
| Payments | Stripe + PayPal (international) · Telebirr + CBE Birr (Ethiopia) |
| Database | PostgreSQL (structured data) + AWS S3 (media: audio, video, documents) |
| Infrastructure | AWS/GCP, CloudFront CDN + Ethio Telecom edge, 99.9% uptime SLA |
| Integrations | Google Maps · YouTube/Facebook Live · SendGrid · Firebase Push Notifications |

Each of the four pillars (Give, Find, News, Academy) is a self-contained module sharing only: user auth, the design system, the notification pipeline, and the search index.

PART 3 — PHASED ROADMAP (36 MONTHS)

The most important rule: Phase 1 must be live and stable before Phase 2 begins. Never build on an unstable foundation.

| PHASE 1 — Foundation Months 1–8 | Rebuild, Migrate, Launch |
| --- | --- |

## Goal

Replace the 2003 website with a modern, mobile-first platform. Migrate all content. Launch donation portal and basic church finder.

## Month-by-Month Plan

| Months | Focus | Key Work |
| --- | --- | --- |
|  | Setup | Assemble team, provision infrastructure, install Strapi CMS, define design tokens, begin Ge'ez rendering tests |
|  | Content Migration | Migrate Bible (81 books), Zema audio, liturgical texts, church history, prayer books into CMS |
|  | Core Build | Build homepage, Scripture reader, Zema player, liturgical calendar, fasting guide, user accounts |
|  | Giving + Finder + Launch | Build Donation Portal (Stripe + Telebirr + CBE Birr), Church Finder with 50+ parishes, soft launch, public launch |

## Key Deliverables

| # | Deliverable | Month | Priority |
| --- | --- | --- | --- |
| 1.01 | Domain, hosting, SSL |  | Critical |
| 1.02 | Strapi CMS with EOTC permissions |  | Critical |
| 1.03 | Design system: colors, Ethiopic Unicode, components |  | Critical |
| 1.04 | Amharic + English + Ge'ez language switching |  | Critical |
| 1.05–08 | Full content migration (Bible, Zema, liturgy, prayers) |  | Critical |
| 1.09 | Homepage (patriarch banner, daily devotion, pillar cards) |  | Critical |
| 1.10 | Scripture reader (parallel Ge'ez / Amharic / English) |  | Critical |
| 1.11 | Zema audio player + Digital Chant Stand |  | High |
| 1.13 | Liturgical calendar (Ethiopian + Gregorian) |  | Critical |
| 1.16 | User accounts (register, login, profile) |  | Critical |
| 1.18–19 | Donation portal (Stripe, PayPal, Telebirr, CBE Birr) |  | Critical |
| 1.20–21 | Church Finder map with 50 pilot churches |  | Critical |
| 1.22–23 | Performance + accessibility audit (3G test, WCAG 2.1 AA) |  | Critical |
| 1.24 | PUBLIC LAUNCH |  | Critical |

## Phase 1 Launch Criteria (all must be true)

- Site loads in under 3 seconds on a 3G connection in Addis Ababa

- Ge'ez and Amharic render correctly on Android Chrome, iOS Safari, and Windows Edge

- A donor can pay in ETB via Telebirr from a mobile phone

- A parish admin can update service times and post an event without developer help

- All old site content is accessible and the old domain redirects to the new one

- At least one Diocese has reviewed and approved their church directory

| PHASE 2 — Growth | Academy, Full Church Network, News Hub |
| --- | --- |

## Goal

Launch the Tewahedo Academy. Expand to all registered EOTC parishes (700+). Establish the news hub as the authoritative pan-Orthodox source. Formalize the Mahibere Kidusan (MK) partnership.

## Quarter-by-Quarter Plan

| Months | Focus | Key Work |
| --- | --- | --- |
| 9–11 | Academy Setup | Install and theme Moodle LMS. Build Children's (5–12) and Youth (13–18) tracks. Clergy review panel established. |
| 12–14 | Academy Launch + GG Yr 1 | Academy goes live. Gebi Gubaye Year 1 built with MK. Discussion forums and mentor pairing. |
| 15–17 | Full Church Network | All 700+ parishes onboarded. Events system launched. Live stream links per church. |
| 18–20 | News Hub | EOTC news section + pan-Orthodox feed. Weekly newsletter (SendGrid). Digital magazine launched. |
| 21–22 | GG Yrs 2–3 + Adult Track | Gebi Gubaye Years 2 & 3 published. Adult/Catechumen track built. Live webinar platform. |

## Key Deliverables

| # | Deliverable | Month | Priority |
| --- | --- | --- | --- |
| 2.01 | Moodle LMS installed, themed, integrated with user accounts |  | Critical |
| 2.02–03 | Children's Track (12 modules) + Youth Track (12 modules) |  | Critical |
| 2.05 | Tewahedo Academy public launch |  | Critical |
| 2.06 | Gebi Gubaye Year 1 curriculum (with MK) |  | Critical |
| 2.09 | Offline content download for low-connectivity users |  | Critical |
| 2.11 | Full church database: 700+ parishes onboarded |  | Critical |
| 2.12 | Events calendar: church-level posting, RSVP, reminders |  | Critical |
| 2.16 | EOTC official news section |  | Critical |
| 2.18 | Weekly email newsletter (SendGrid) |  | High |
| 2.22–23 | Gebi Gubaye Years 2 & 3 + Adult/Catechumen track |  | High |
| 2.25 | Push notifications (Firebase): feasts, synod alerts, events |  | High |

## Phase 2 Success Criteria

- 2,000+ registered Academy students within 60 days of launch

- 700+ churches in database covering all 14 Ethiopian dioceses + major diaspora hubs

- Gebi Gubaye Year 1 formally endorsed by MK Sunday School Department

- 5,000+ newsletter subscribers within 3 months of launch

| PHASE 3 — Maturity | Mobile Apps, Full Curriculum, Global Scale |
| --- | --- |

## Goal

Native mobile apps, full Gebi Gubaye curriculum, multi-language expansion, advanced giving, 360° virtual tours, and pan-Orthodox partnerships. By Month 36: the most complete Orthodox Church digital platform in Africa.

## Key Deliverables

| # | Deliverable | Month | Priority |
| --- | --- | --- | --- |
| 3.01 | Native Android app (React Native, full feature parity) |  | High |
| 3.02 | Native iOS app (React Native, full feature parity) |  | High |
| 3.03 | Gebi Gubaye Year 4 curriculum |  | High |
| 3.04–05 | Graduate track (patristics, Ge'ez literature) + Clergy track |  | Medium |
| 3.06 | Tigrinya language expansion (all core content) |  | High |
| 3.07–08 | Oromo + French language expansion |  | Medium |
| 3.09 | 360° virtual tours: Lalibela, Aksum, Debre Damo, Holy Trinity |  | Medium |
| 3.11 | Tax receipt automation: US 501(c)(3), UK Gift Aid, Canada CRA |  | High |
| 3.16 | Offline mode (full PWA): Bible, prayer, and courses downloadable |  | High |
| 3.14–15 | Content partnerships: Coptic, Armenian, and Syriac Orthodox churches |  | Medium |
| 3.18 | Platform public launch celebration — 36-month review |  | Critical |

PART 4 — UI DESIGN GUIDE

# 5. Design Foundations (Before Any Screen)

Complete all six steps below before designing any screen. Estimated time: 2–3 weeks.

| Step | Task | Detail |
| --- | --- | --- |
| D1 | Color System | Navy #1A3A5C (primary), Gold #C8A84B (accent), Gold-light #FFF8E7 (backgrounds), Gray #F5F5F5 (surfaces) |
| D2 | Typography | Noto Serif Ethiopic for Amharic/Ge'ez. Arial/Inter for UI. 5 text sizes. Test Ge'ez on Android + iOS before proceeding. |
| D3 | Spacing & Grid | 8-point grid. Max-width 1200px. Breakpoints: mobile 375px, tablet 768px, desktop 1200px. Design mobile-first. |
| D4 | Component Library | Build in Figma: Button, Input, Card, Badge, Nav Bar, Sidebar, Modal, Table Row, Avatar, Audio Player, Progress Bar |
| D5 | Cross Motif | Commission 3 Ethiopian cross SVGs (Meskel, Lalibela, Processional) as decorative elements. |
| D6 | Icon Set | Icons for: Church, Tabot, Zema, Fasting, Feast, Donation, Calendar, Monastery, Cross, Liturgy. Base: Tabler Icons. |

Or can be modified if the chooses to.

# 6. Design Priority Order by Phase

## Phase 1 — Design Screens

| Screen | Components | Month |
| --- | --- | --- |
| D1.1 Homepage | Patriarch hero, daily devotion strip, four-pillar cards, feast countdown, news strip |  |
| D1.2 Global Navigation | Top nav, mobile menu, language switcher |  |
| D1.3 Scripture Reader | Book navigator, parallel Ge'ez/Amharic/English columns, audio controls |  |
| D1.4 Zema Player + Chant Stand | Library, player controls, large-text view for cantors |  |
| D1.5 Liturgical Calendar | Month grid, feast/fast color coding, day detail panel, ICS download |  |
| D1.6 Church Finder | Map (60%), filter panel, results list (40%), church detail panel |  |
| D1.7 Donation Form | Amount selector, church picker, payment methods, review + confirm |  |
| D1.8 User Account | Login, register, profile, settings |  |

## Phase 2 — Design Screens

| Screen | Components | Month |
| --- | --- | --- |
| D2.1 Academy Home | Track selector cards, progress overview, upcoming webinar banner |  |
| D2.2 Course Detail | Lesson list, progress bar, locked/unlocked states |  |
| D2.3 Lesson View | Video player, text content, quiz section, discussion, navigation |  |
| D2.4 Certificate | Downloadable PDF with EOTC + MK seal |  |
| D2.5 Events Calendar | Church event listing, event detail page |  |
| D2.6 News Hub | Article list, category filters, article detail |  |
| D2.7 Campaign Page | Progress bar, donor list, share buttons |  |
| D2.8 Parish Admin Dashboard | Manage profile, events, giving campaigns |  |

TEAM, BUDGET & RISK

# 7. Team Structure

| Role | FTE | Responsibility |
| --- | --- | --- |
| Project Manager | 1 FTE | Roadmap, coordination, timeline and budget management |
| Lead Architect / Backend | 1 FTE | System architecture, database, API, CMS, payments |
| Frontend Developer | 1–2 FTE | All web screens, design system, accessibility |
| UX/UI Designer | 1 FTE | Design system, all screens and mockups |
| Content Team | 2–3 FTE | Migration, editorial, multilingual (must include Amharic + Ge'ez literacy) |
| Mobile Developer | 1 FTE (Phase 3) | iOS and Android apps |
| MK Partnership Lead | Part-time | Academy curriculum coordination |
| Clergy Review Panel | 3–5 clergy | Review and approve all theological content |
| QA Engineer | Part-time | Testing on Ethiopian devices, payments, accessibility |

# 8. Key Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Ge'ez rendering failures | Typography tested in Month 2 — nothing proceeds until confirmed on all target devices |
| Telebirr API delays | Submit API application in Month 1. Stripe/PayPal as fallback for Phase 1 launch. |
| Low-bandwidth performance | 3G testing is a Phase 1 launch criterion. CDN edge nodes in Ethiopia. |
| Content quality | Dedicated content team + clergy review panel. No module ships without review. |
| Church database quality | Diocese Admins own their listings. 50 pilot churches in Phase 1 build trust. |
| MK partnership breakdown | Formal MOU signed before Phase 2 begins. MK owns content; platform delivers it. |
| Scope creep | Strict phase gating. No Phase 2 work until Phase 1 criteria met. New features need Steering Committee approval. |

WHAT TO DO NEXT — WEEK 1 ACTIONS

If approved by the Steering Committee, these actions must start in Week 1:

## Governance

- Form the Steering Committee and appoint the Project Manager

- Issue letter of intent to Mahibere Kidusan for Academy partnership

## Technology

- Register the domain, provision cloud hosting (AWS or GCP), set up GitHub repository

- Install Strapi CMS on the staging server

## Design

- Hire the UI/UX Designer and brief them on this document

- Begin the 6 design foundation steps (D1–D6) immediately

## Content

- Audit all existing ethiopianorthodox.org content — catalog everything to be migrated

- Identify Amharic- and Ge'ez-literate editors for the content team

## Payments

- Submit Telebirr API application to Ethio Telecom now — approval takes time

- Create Stripe account and PayPal nonprofit account

## Pilot Churches

- Identify 5 Diocese Admins to be first to onboard — their feedback shapes Phase 2

☦  ☦  ☦

Ethiopian Orthodox Tewahedo Church  —  Digital Platform Roadmap